Agenda Item 8

| Report to: | East Sussex Strategic Partnership (ESSP) |
| --- | --- |
| Date: | 27 November 2008 |
| Title: | Local Area Agreement (LAA) Annual Review/Refresh |
| Author: | Alison Horan, Head of Community Partnerships, ESCC |
| Purpose: | To outline the process and timetable for the first review of the new LAA (LAA2) |
| Recommendation That the East Sussex Strategic Partnership Executive Board: Note the Government’s expectations and timetable for the LAA Annual Review, and Consider whether there is any particular negotiating stance the Partnership wishes to adopt, with special consideration to the impact on the LAA of the economic downturn and agree the proposed Governance arrangements. |

- Background

  - The new East Sussex LAA (LAA 2) was approved by Government on 30 June 2008, with a retrospective start from April 2008. Our new LAA contains 33 targets and 16 mandatory educational achievement targets set by the Department for Schools and Families. All targets are drawn from the National Indicator Set introduced earlier this year. Because of the required speed of development, some of the indicators were either not fully defined, or baseline information was not available at the time of finalising the LAA 2. In the new East Sussex LAA there are seven such indicators, known as ‘Placeholders’.

  - Government has an expectation that there will be an annual review of every LAA. On 22 September the guidance for the 2008/09 review was published, it can be accessed via this link and key points are summarised below.

- Because of the number of targets not concluded at original sign off of the LAA 2 there will be a distinct ‘refresh’ element to the annual review for this year only.

- The refresh largely relates to ‘unfinished business’ from the previous negotiations relating to delayed indicators, revised indicators and targets inconsistent with their indicator definition.

- The review takes place this year in the context of limited delivery data.

- The annual review’s purpose is to refine targets not replace them.

- Any other revisions to the LAA 2 are ‘by exception’ where circumstances have changed and based on evidence.

- In the absence of significant delivery data the review will look at capacity and delivery arrangements.

  - In addition to the requirements for Review/Refresh required by Government/GOSE, there are local issues that Partners and individual indicator leads will wish to see included in the Review process. There are two that are significant. The first is an acknowledgement and possible adjustment to targets impacted by the economic downturn/ recession. These initially include the targets for housing, economic development and employment, with potential longer term effects on a much wider set of targets including crime reduction, community cohesion and health. However any such revisions will need to be based on robust evidence. The second is delivery by Government and its agencies on its contribution to achieving targets, e.g. Highways agency and Job Centre Plus.

- Process and Timetable

  - The Review Guidance sets out key milestones in order to achieve, by April 2009, an approved revised LAA. This, together with key local meeting dates, forms the initial timetable detailed below. This will obviously be added to as the process gathers pace.

Key Milestones (GOSE/ National requirements in bold)

| October to January | Annual review discussions with GOSE |
| --- | --- |
| 12 November | LAA Project Team meeting 9.30am-11.00am Council Chamber |
| 17 November 2008 | Performance Report to GOSE (see 2.3 below) |
| 27 November 2008 | Performance Report on LAA Quarter 2 to ESSP |
| 11 December | LAA Project Team meeting 11.15am-12.45pm Council Chamber |
| 16 January 2009 | LAA Project Team 9.30am-11.00am Council Chamber |
| 13 February 2009 | LAA Project Team 9.30am-11.00am Council Chamber |
| 16 February 2009 | Baseline data for Place Survey indicators (NI1 & NI4) available from the Audit Commission |
| 2 March 2009 | Refreshed LAA to GOSE |
| 12 March 2009 | Formal endorsement of LAA Review/Refresh to ESSP |
| 26 March 2009 | Endorsed and refreshed LAA submitted to GOSE |
| 27 March 2009 | GOSE submit LAA to Secretary of State for approval |
| Early April | Secretary of State approves revised LAA |

  - Eileen MacDonald, the East Sussex Locality Lead from GOSE has given an indication of the indicators that GOSE consider require further work and the LAA Project Team met in October to consider other outstanding areas. This has resulted in a list which is attached at Appendix A.  In addition GOSE are awaiting ‘Target Negotiation Briefs’ (TNBs) from central Government to enable them to negotiate on unresolved ‘Placeholder’ indicators; also expected, possibly as part of the TNBs is a position statement on LAAs and the economic downturn.

  - It has been agreed with GOSE that the Performance Report required by 17 November will consist of the Performance Report for Quarter 2 of the LAA 2 considered as another item on today’s agenda.

  - The relevant Indicator Leads will take responsibility for negotiating their own targets in conjunction with any key partners and/or partnerships. The need to reconvene the Project Board will be kept under review. As the final draft of the Review/Refresh is due for submission to GOSE before the next ESSP Executive meeting, the draft refresh will be circulated to Executive Board members for comment before the 2 March submission.

- Recommendations

  - The Executive Group consider whether there is any particular negotiating stance the Partnership wishes to adopt, with special consideration to the impact on the LAA of the economic downturn.

Appendix A

LAA 2 Refresh/Review – Targets requiring further work	October 2008

| NI | Definition | Lead Officer | Action |
| --- | --- | --- | --- |
| 1 | % of people who believe people from different backgrounds get on well together in their local area (Hastings) | Mary Denning Hastings Borough Council | Baseline and targets to be set following Place Survey. Data available from AC by 16.2.2009 |
| 4 | % of people who feel that they can influence decision in their locality | Jane Mackney ESCC | Baseline and targets to be set following Place Survey Data available from AC by 16.2.2009 |
| 19 | Rate of proven re-offending by young offenders | John Hawkins ESCC | Baseline and targets to be set |
| 20 | Assault with injury crime rate | Samanatha Coates Sussex Police | Baselines to be confirmed by Home Office and year 2 & 3 targets set |
| 30 | Re-offending rate of prolific and priority offenders | Andrea Saunders Sussex Probation | New targets for year 2 to be negotiated in April/May 2009 & for year 3 in April /May 2010 |
| 32 | Repeat incidents of domestic violence | Marcus Gomm ESCC | CLG consultation on deferred indicators to 31/10/2008. Baseline and targets to be set. |
| 47 | People killed and seriously injured in accidents | Colin Clarke ESCC | Original LAA suggests review as part of refresh because of challenging nature of target |
| 110 | Young people’s participation in positive activities | Colin Edgley ESCC | Baseline and targets to be set from Tellus survey in the autumn |
| 118 | Take up of formal childcare by low income working families | Mel Shires ESCC | Spatial level, baselines and targets to be set by Jan 2009 &/or consider whether to replace with 116 |
| 123 | Stopping smoking | Stuart Ramsbottom Hastings& Rother PCT | CLG proposing changes to definition consultation to 31/10/2008 |
| 130 | Social care clients receiving Self Directed Support per 100,000 population | Jaine Huntley ESCC | CLG proposing changes to definition consultation to 31/10/2008 |
| 154 | Net additional homes provided | Stephen Walker Lewes District Council | Review due to economic downturn |
| 155 | Number of affordable homes delivered (gross) | Ian Fitzpatrick Eastbourne Borough Council | Review due to economic downturn |
| 159 | Supply of ready to develop housing sites. | Stephen Walker Lewes District Council | Review due to economic downturn |
| 171 | New business registration rate | Kieran McNamara ESCC | Baseline due Oct/Nov 2008 and targets to be set between Nov 2008-Feb 2009 Review due to economic downturn |
| 175 | Access to services and facilities, public transport, walking and cycling | James Harris ESCC | Review baseline and targets |
| NB. With the Government announcement that Key Stage 3 tests are to be dropped the following mandatory indicators are to be dropped immediately: NI 74 NI 83 NI 95 NI 96 NI 97 NI 98 All remaining mandatory DCSF indicators to have year 2 targets set in Autumn. |

GOSE have confirmed that they are happy for NI 169 – Roads Maintenance to be included in the LTP rather than included in the LAA 2 refresh.